## User Story
Issue type | Summary | Description
|  | Objective | Acceptance
Story | Events in Calendar | As a registered user, when login I want to view the calendar month wise, week wise or day wise so that I can view events and create new events. | Acceptance 1: On clicking 'Month' user can view month wise events. Acceptance 2: On clicking 'Week' user can view week wise events. Acceptance 3: On clicking 'Day' user can view day wise events. Acceptance 4: On clicking 'Agenda' user can view events in the particular range. Acceptance 5: On clicking 'Today' user van view today’s events. Acceptance 6: On clicking 'Sync Now' all the events created should be reflected on calendar page. Acceptance 7: On clicking 'New' user should be redirected to create new event page.
Story | Create New Event | As a registered user I can create new event in calendar so that I can prepare for the events. | Acceptance 1: User can create events by clicking on New button on calendar page. Acceptance 2: In Create new event page On the top there should be cancel and Save button. Acceptance 3: In Create new event page there should be details like Title, Calendar, Start Date, End Date, Category, Tags, Description, Location, Deal, Task, Case, Alert, Reminder Time, Assigned to, Participants, Company, Recurrence and Identifier. Acceptance 4: Title and Calendar should be mandatory. Calendar should have valid google account linked. Acceptance 5: Start date and end date should display current date by default Acceptance 6: As I click on Category field it should Show the suggestions in dropdown. Acceptance 7: As I click on Tags field it should be able to search already created tags. Acceptance 8: In Description field I should be able to enter more than one line. Acceptance 9: In Location field I should be able to enter location with more than one line. Acceptance 10: For All Day event slider should be toggle on or off. Note: It should be off by default. Acceptance 11: As I click on deals field it should be able to search already created deals or it should create new deals. Acceptance 12: As I click on Task field it should be able to search already created tasks or it should create new task. Acceptance 13: As I click on Case field it should be able to search already created cases or it should create new case. Acceptance 14: As I click on Alert Before field it should display options with 10 Minutes, 15 Minutes, 30 Minutes, 1 Hour, 2 Hours, 3 Hours. Note: 15 Mins should be default. Acceptance 15: As I click on Alert Via field it should display options with Desktop, Email, SMS. Note: Desktop should be default. Acceptance 16: As I click on Reminder Time field I should be able to enter Time. Note: User can only enter numbers. Acceptance 17: For Assigned to Field logged in user should be selected defaultly. Acceptance 18: For Referred by there should be suggestion list for the entered contact name. Note: User can enter any Referred by as well by clicking on add . Accptance 19: For Participant field there should be suggestion list. Note: User can add any participant as well. Acceptance 20: As I click on Company field it should display suugestion list of already added companies. Note: User can add any new company as well. Acceptance 21: For Recurrence there should be to options 'No recurrence. Click to set.' and 'Clear' option. Acceptance 22: As I click on 'No recurrence. Click to set.' a new window should with name 'Edit Event Recurrence' should appear having options like Interval, Days, Interval, Times and End At. Acceptance 23: In Edit Event Recurrence page there should be two options Cancel and Set in the bottom. As I click on Set button It should Set the event recurrence. Acceptance 24: As I click on Internal it should display drop down list with options like Daily, Weekly, Monthly and Yearly. Note: Weekly should be default. Acceptance 25: As I click on Days it should display drop down list with options like Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday. Acceptance 26: As I click on Interval i should be able to enter intervals. Note: Default interval is 1. Acceptance 27: As I click on End At field it should display Date and Time field. Acceptance 28: As I click on Identifier I should be able to select the desired valid email id's from the drop down section. Acceptance 29: After clicking on Cancel, I should redirect to main Calendar page. Acceptance 30: After clicking on Save, I should redirect to main Calendar page and new event should be reflected in calendar.

## Test Scenario
Story name | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
Events in Calendar | TS_01 | COG-50 | To veirfy on calender weather the created tasks are reflecting on calender page. | UI | 1 | Need to check Month, Week, Day, Agenda, Today and Sync Now buttons.
Create New Event | TS_02 | COG-52 | To add New event | Functional | 3 | 1. Creating new event by entering valid details like Title, Calendar, Start Date, End Date, Category, Tags, Description, Location, Deal, Task, Case, Alert, Reminder Time, Assigned to, Participants, Company, Recurrence and Identifier. 2. Creating new event keeping mandatory fields blank. 3. Creating new event by giving invalid Calendar.

## Test Case
Test Case ID | Story/Folder | Objective | Precondition | Test Name | Test Case Steps | Priority | Test Data | Expected Result | Actual Result | Status
TC_Event_01 | /Events in Calendar | To veirfy the Calendar page. | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Veirfy Calendar page | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar | High |  | It should display Calendar page | Displays Calendar page | Pass
TC_Event_02 | /Events in Calendar | To verify the Month button. | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify Month button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on Month button | Medium |  | It should display events month wise | Display events month wise | Pass
TC_Event_03 | /Events in Calendar | To verify the Week button. | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify Week button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on Week button | Medium |  | It should display events week wise | Display events week wise | Pass
TC_Event_04 | /Events in Calendar | To verify the Day button. | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify Day button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on Day button | Medium |  | It should display events day wise | Display events day wise | Pass
TC_Event_05 | /Events in Calendar | To verify the Today button | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify Today button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on Today button | Medium |  | It should display today's events | Display today's events | Pass
TC_Event_06 | /Events in Calendar | To verify the Agenda button. | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify Agenda button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on Agenda button | Medium |  | It should display events in the particular range | Display events in the particular range | Pass
TC_Event_07 | /Events in Calendar | To verify the New button | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify New button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button | High |  | It should display the page to create new events | Display the page to create new events | Pass
TC_Event_08 | /Events in Calendar | To verify the Sync Now button. | 1. URL https://freecrm.co.in/index.html should be working 2. User should be registered | Verify Sync Now button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on Sync Now button | High |  | It should Sync All the events created and display them on calendar | It Syncs All the events created and display them on calendar | Pass
TC_New_09 | /Create New Event | To verify the New option | 1.User should be logged in. 2.Calendar page should be opened 3.There should be New button at top right | Verify the New option. | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button | Normal |  | In Create new event page there should be details like Title, Calendar, Start Date, End Date, Category, Tags, Description, Location, Deal, Task, Case, Alert, Reminder Time, Assigned to, Participants, Company, Recurrence and Identifier. | Displays details like Title, Calendar, Start Date, End Date, Category, Tags, Description, Location, Deal, Task, Case, Alert, Reminder Time, Assigned to, Participants, Company, Recurrence and Identifier. | Pass
TC_New_10 | /Create New Event | To verify the Title option | 1.User should be logged in. 2.Create New Event page should be opened. | Verify the Title field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Title | High | TaskName | User should be able to enter the alphanumeric characters. | User is able to enter the alphanumeric characters. | Pass
TC_New_11 | /Create New Event | To verify the Calendar | 1.User should be logged in. 2.Create New Event page should be opened. | Verify the Calendar field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Calendar | High | ashwinij997@gmail.com | User should be able to enter the Calendar. | User is able to enter the Calendar. | Pass
TC_New_12 | /Create New Event | To verify the Calendar with Invalid Data | 1.User should be logged in. 2.Create New Event page should be opened. | Verify the Calendar field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Calendar | High | s1 | "Calendar Should have linked to valid google account" should be displayed as an alert message. | "Calendar Should have linked to valid google account" is displayed as an alert message. | Pass
TC_New_13 | /Create New Event | To verify Start date | 1.User should be logged in. 2.Create New Event page should be opened. | Verify the Start date | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Start Date | High |  | User Should be able to selcet desired date and time | User is able to selcet desired date and time | Pass
TC_New_14 | /Create New Event | To verify End date | 1.User should be logged in. 2.Create New Event page should be opened. | Verify the End date | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on End Date | High |  | User Should be able to selcet desired date and time | User is able to selcet desired date and time | Pass
TC_New_15 | /Create New Event | To verify Category | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Category field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Category | Normal |  | Category field should Show the suggestions like Important, Opportunity, Optional, Critical, Meeting, Social, Time Off, Private in dropdown. | Category field shows the suggestions like Important, Opportunity, Optional, Critical, Meeting, Social, Time Off, Private in dropdown. | Pass
TC_New_16 | /Create New Event | To verify Tags Field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Tags Field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Tag | Normal |  | Tags field should be able to search already created tags or able to add new tags. | Tags field is able to search already created tags or able to add new tags. | Pass
TC_New_17 | /Create New Event | To verify Description and Location field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Description and Location field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Description/Location | Normal |  | When the user clicks on Description / Location the user should be able to add the data with alphanumeric characters as well. | When the user clicks on Description / Location the user is able to add the data with alphanumeric characters as well. | Pass
TC_New_18 | /Create New Event | To verify All Day field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify All Day field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on All Day | Normal |  | For All Day event slider should be toggle on or off. It should be off by default. | For All Day event slider is toggle on or off. It should be off by default. | Pass
TC_New_19 | /Create New Event | To verify Task, Deal, Case fields | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Task, Deal, Case fields | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Task/Deal/Case | Normal |  | As I click on Task/Deal/Case field it should be able to search already created tasks/Deals/Cases or it should create new task/deal/case. | As I click on Task/Deal/Case field it is able to search already created tasks/Deals/Cases and able to create new task/deal/case. | Pass
TC_New_20 | /Create New Event | To verify Alert Before field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Alert Before field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Alert Before | Normal |  | It should display options with 10 Minutes, 15 Minutes, 30 Minutes, 1 Hour, 2 Hours, 3 Hours. 15 Mins should be selected by default. | It displays options with 10 Minutes, 15 Minutes, 30 Minutes, 1 Hour, 2 Hours, 3 Hours. 15 Mins should be selected by default. | Pass
TC_New_21 | /Create New Event | To verify Alert Via field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Alert Via field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Alert Via | Normal |  | As I click on Alert Via field it should display options with Desktop, Email, SMS. Desktop should be selected by default. | As I click on Alert Via field it displays options with Desktop, Email, SMS. Desktop is selected by default. | Pass
TC_New_22 | /Create New Event | To verify Reminder Time field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Reminder Time field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Reminder Time | Normal |  | As I click on Reminder Time field I should be able to enter Time in HrMin format. User can only enter numbers. | In Reminder Time field I'm able to enter many numbers. The field don’t have validation for time field. | Fail
TC_New_23 | /Create New Event | To verify Assigned to field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Assigned to field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Assigned To | Normal |  | Logged in user should be selected defaultly. | Logged in user is selected by default. | Pass
TC_New_24 | /Create New Event | To verify Referred by/Participant/Comapny field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Participant/Comapny field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Referred by/Participant/Comapny | Normal |  | There should be suggestion list for the entered contact name/paricipant/company. User can enter any Referred by as well by clicking on add . | There is suggestion list for the entered paricipant/company. I can enter any Referred by as well by clicking on add . | Pass
TC_New_25 | /Create New Event | To verify Recurrence field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Recurrence field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Recurrence | Normal |  | As I click on 'No recurrence. Click to set.' a new window should with name 'Edit Event Recurrence' should appear having options like Interval, Days, Interval, Times and End At. | As I click on 'No recurrence. Click to set.' a new window with name 'Edit Event Recurrence' appears having options like Interval, Days, Interval, Times and End At. | Pass
TC_New_26 | /Create New Event | To verify Edit Event field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Edit Event field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Edit Event | Normal |  | In Edit Event Recurrence page there should be two options Cancel and Set in the bottom. As I click on Set button It should Set the event recurrence. | In Edit Event Recurrence page there are two options Cancel and Set in the bottom. As I click on Set button It should Set the event recurrence. | Pass
TC_New_27 | /Create New Event | To verify Internal field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Internal field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Verify Internal | Normal |  | As I click on Internal it should display drop down list with options like Daily, Weekly, Monthly and Yearly. Weekly should be selected by default. | As I click on Internal it displays drop down list with options like Daily, Weekly, Monthly and Yearly. Weekly should be selected by default. | Pass
TC_New_28 | /Create New Event | To verify Days field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Days field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Days | Normal |  | As I click on Days it should display drop down list with options like Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday. | As I click on Days it displays drop down list with options like Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday. | Pass
TC_New_29 | /Create New Event | To verify Interval field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Interval field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Interval | Normal |  | As I click on Interval i should be able to enter intervals. Default interval is 1. | As I click on Interval I'm able to enter intervals. Default interval is 1. | Pass
TC_New_30 | /Create New Event | To verify End At field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify End At field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on End At | Normal |  | As I click on End At field it should display Date and Time field. | As I click on End At field it displays Date and Time field. | Pass
TC_New_31 | /Create New Event | To verify Identifier field | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Identifier field | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Identifier | Normal |  | As I click on Identifier I should be able to select the desired valid email id's from the drop down section. | As I click on Identifier I'm able to select the desired valid email id's from the drop down section. | Pass
TC_New_32 | /Create New Event | To verify Save button | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Save button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Save | High |  | When the user clicks on save all the entered data should be saved and summary should appear with all the details. | When the I clicked on save all the entered data was saved and summary appeared with all the details. | Pass
TC_New_33 | /Create New Event | To verify Cancel button | 1.User should be logged in. 2.Create New Event page should be opened. | Verify Cancel button | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Cancel | High |  | When the user clicks on Cancel all the entered data should be discarded and the user is directed to the Calendar page. | When the I clicked on Cancel all the entered data was discarded and the I was directed to the Calendar page. | Pass
TC_New_34 | /Create New Event | Verify when no data is entered in Title field or Calendar field and Save button is pressed | 1.User should be logged in. 2.Create New Event page should be opened. | Check if same page is displayed when no title and calendar is entered and Save button is pressed | 1. Open the URL https://freecrm.co.in/index.html 2. Enter details and click on Login 3. Click on Calendar 4. Click on New button 5.Click on Save | High |  | "Validation Error: Title is required. Calendar is required" should be displayed as an alert message. | "Validation Error: Title is required. Calendar is required" is displayed as an alert message. | Pass

## Defect Report
Defect ID | Summary | ReportedBy | Date | Assigned To | Severity | Priority | Status | Module | Build Version | Reprodecable | ReproSteps
COG-62 | In Reminder Time field I can enter many numbers. The field don’t have validation for time field. | ashwini.c.jadhav@capgemini.com | 2020-12-02 | abc@capgemini.com | Normal | Normal | To Do | Create New Event | Sprint 1 | Yes | 1. Login into your account 2. Goto Calendar page 3. Click on New 4. Click on Reminder Time

## Test Summary Report
Test Summary Report for Sprint1 (27 - Nov to 02-Dec )
S.No. | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 10
2 | Created TestCases | 130
3 | No. of tests Executed in Sprint ,iteration 1 | 130 | 123 | 7
4 | Defects Reported | 6
5 | No. of Sprints Executed | 1
Any Challenges
Any Best Practises

## Burn Down Chart
Burn Down Chart

## Sprint Report
Sprint Report